## list
		sheet					register	*
	1	tasks					20/05/08 14:52	*
	2	qs					20/05/08 14:52	*
	3							*
								*
								*
								*
								*
								*
								*
								*
								*
								*
*	*	*	*	*	*	*	2020/9/18 12:02	*

## 1_tasks
status	sn(48.1)	genre	description	platform	session id	register	started	comp		*
*	1		trailing ==> coding	mt4		20200414_154231	20/05/05 10:22	20/05/05 13:45		*
#	1a	work	trailing : TP update ==> if Bid > initial TP → new SL will be (orig.SL – X amount)			05.05				*
*	2		1. when ordering → ticket num : write to a file “[ea-4].(2020XXXX_XXX).dat” / 2. also : prev-10 bars, BB area number / ==> EXEC:@TASKS-5	mt4		20200414_154231		20/05/04 16:27		*
*	3	new FUNC	get_BB_Loc_Num(int index) : int num_BB_Area	mt4		20200414_154231		20200415_133912		*
*	4	new FUNC	get_BB_Loc_Nums(int lenOf_Bars, int num_Start_Index) : int lo_BB_Area_Nums[]	mt4		20200415_134059		20/04/21 17:34		*
*	5	work	when ordering, write out data / ticket num / BB zone nums	mt4		20/04/20 14:34		20/05/04 16:26		*
*	5a	work	when ordering, write out data / ==> bar width level	mt4		20/05/03 15:24		20/05/04 16:26		*
*	6	new FUNC	op_Get_BB_Loc_Nums()	mt4		20/04/20 17:02	-	20/04/20 17:05		*
*	7	work	when new bar ==> write out BB zone data	mt4		20/04/20 17:29				*
*	8	modify FUNC	get_BB_Loc_Nums(...), op_Get_BB_Loc_Nums / ==> add param / _lo_Up_Down[]	mt4		20/04/21 09:34		20/04/21 10:05		*
*	9	modify FUNC	get_BB_Loc_Nums(...), op_Get_BB_Loc_Nums / ==> add param / float _lo_WidthOf_Up_Down[]	mt4		20/04/21 10:04		20/04/21 17:33		*
*	10	modify	“bar-data” file ==> add info / 1) pair, period	mt4		20/04/21 17:33		20/04/22 12:21		*
*	11	new feature	when new bar ==> write out : stats / 1) width of up/down	mt4		20/04/21 17:49		20/04/22 14:58		*
*	12	modify FUNC	get_BB_Loc_Nums(...), op_Get_BB_Loc_Nums / ==> add param / int _lo_WidthOf_Up_Down__Zone_Num[] / ==> 2. get_LO_Width_Zone_Nums / if : M1 (//_20200422_143448:mark : lib_ea_2.mqh) / 0.005>= 1 / 0.01>= 2 / 0.015>= 3 / 0.02>= 4 / 0.03>= 5 / 0.03< 6	mt4		20/04/22 14:35		20/04/24 17:58		*
#	13	tools	new FUNC : slice_Raw_Data_By_Week	php	44# 10.3.3	04.25				*
*	5a	tools	ticket-data log file ==> write header lines in “init()”	mt4	44# 11.1_7	20/04/28 15:10		20/09/18 12:02		*
*	14	coding	bar width level : vals ==> to cons.mqh / ==> A/J,M1 → comp : cons_LO_Threshold_Bar_Width_Level_A_J_M1	mt4	JVEMV6 44# 11.1_11	20/05/02 13:09		20/05/04 16:29		*
*	15	new FUnC	get_Bar_Width_Level_Nums(int index, float lo_Level_Vals) : int num_Level	mt4	JVEMV6 44# 11.1_11	20/05/02 13:34		20/05/03 15:07		*
#	16	work	lo_Thresholds ==> init according to : Period(), Symbol() / //20200503_151441:tmp / ea-4.mq4	mt4		05.03				*
#	17	work	gen ==> trade result list / 1) use / 1. trading report / 2. [ea-4_tester-1].(XXX).(tickets-data) / 2) resources / 1. get_ListOf_Orders_From_Statement() (\FxUtilitiesController.php)	mt4		05.05				*
#	18	review	combined data / [ea-4_tester-1].(20200507_140530).(combined-data).(20200507_175651_379914).dat / C:\Users\iwabuchiken\AppData\Roaming\MetaQuotes\Terminal\34B08C83A5AAE27A4079DE708E60511E\MQL4\Files\Logs\20200505_140459[eap-2.id-1].[AUDJPY-5].dir	mt4		05.07	05.08			*
#	19	work	gen “combined-data”	php		05.09				*
#	19.1	work	“combined-data” ==> process data	sheet		20/05/10 15:25				*
#	20	work	gen stat data / 1. of “combined-data” ==> BB.loc-1が Z1~6のものについて / 2. ==> “Profit” の合計、算出してみよう (Z1、Z2、...それぞれの領域について）	-	44#10.3.4_4	05.09				*
#	21	work	BB.loc-X を、X=1から順に、ソートする / ==> log_JVE_44_10_3_4.[session-3].ods		10.3.4_6	05.13				*
#	22	admin	desktop-pcで作ったEAファイル => note-pcへ入れる			05.15				*
#	23	work	“width level” data ==> generate / for / 1. U/J / 2. E/J		44#10.4_7	05.16				*
*	24	prog	ea-4.mq4 ==> gen other data → technical data : Force. RSI, MFI / => tickets-data log data / ==> prev 9 bars	mt4	44#13.24_1	20/05/18 12:32		20/05/18 15:18		*
#	25	stats	“(stats-data)” file / ==> write more stats data / 1) Force index : between-X-bars diff of Force vals (X = 2, for starter) / 2) same to ==> MFI, RSI	mt4	44#13.24_1	05.18				*
*	26	admin	gen trading result list (combined list) / ==> as for param vals, → use external file / ===> 44#13.26_2	php	44#13.26	20/05/19 18:53		20/05/20 13:50		*
#	26	admin	note-pcで作ったstatement file 他 => desktop へ入れる	-	-	05.20				*
#	27	observe	trade result list (mfi, rsi included) ==> observe	-	-	05.20				*
#	28	tools	gen raw data / ==> more data (indicator values) / ==> MFI,Force,RSI / 2) coding / 1. mt4 / 2. php	mt4	-	05.21				*
#	28.1	func	get_ListOf_BarDatas__V2()	php	-	05.22				*
#	13a	tools	new FUNC : LibFxAdmin::slice_Raw_Data_By_Day__V2 / 1. slice / 2. return values / 3. caller(_slice_Raw_Data_By_Day : FxAdminController) ==> write to file	php	-	05.24				*
#	13b	tools	slice_Raw_Data (//_20200522_115734:head FxAdminController) / ==> use url parameters / 1. source csv file name	php	-	05.26				*
#	29	tools	fx_tester_T_1_V2	php	-	05.27				*
#	29.1	tools	fx_tester_T_1__Order_Buy__V2()	php	-	05.27				*
#	29.2	tools	fx_tester_T_1__Order_Buy__V2() / get : list of bardatas	php	-	05.29				*
#	30	coding	for-loop ended with ==> j3-3 : Y : 1 / for-loop ended with ==> j3-1 : 2 : Y : 1 / ===> post for-loop coding	php		07.09				*
#	31	coding	log file (dat file) / loc in BB ==> 5 prev ones before the starting bar	php		07.13				*
#	32	coding	tester_1__V2 ==> この tester を動かして、 / SL, TP の設定（$sumOf_Plus, $sumOf_Minus ==> 最大に近くなる値の組み合わせ） => 他の期間も、データを使って、導出しよう	php		07.13				*
#	33	coding	ISSUE ==> first loop in for-loop → SL bars ~~> not appended to list of $pos / ==> append to $pos list	php		07.13				*
#	34	coding	“list-of-pos.dat” file ==> new column / ==> according to SL,TP → show gain/loss	php		07.14				*
#	35	coding	“step : 2 : j2 : choice-1 : j3-2 : 1” / ==> 1st bar, TP	php		07.15				*
#	36	admin	gaitame finest ==> デモ口座取得	-		07.19				*
#	37	coding	add / $pos->ext_pr ==> BB zone label	php		07.19				*
#	38	coding	solve problem / id=N6TI	php		07.22				*
#	39	coding	exec tester / ==> fx_tester_T_1_V2 / 1. (slice-by-day).(AUDJPY-M5).(2020-05-13).(20200530_134010_951771).csv / 2. ==> 200 bars	php		07.22				*
#	39.1	coding	exec tester / ==> fx_tester_T_1_V2 / 1. (slice-by-day).(AUDJPY-M5).(2020-05-13).(20200530_134010_951771).csv / 2. ==> all bars	php		07.22				*
#	39.2	coding	exec tester / ==> fx_tester_T_1_V2 / 1. (slice-by-day).(AUDJPY-M5).(2020-05-14).(20200530_134010_951771).csv / 2. ==> all bars	php		07.22				*
#	40	coding	gen combined list / ==> add column names	php		07.22				*
#	41	coding	trailing ==> coding / mode → SELL / prog with ==> new mql file	mt4		07.26				*
#	41.1	coding	//next:20200728_151019:n / new func ==> take_Position__Sell	mt4						*
#	42	sheet	stats ==> more stats / 1) gain sum / loss sum / C:\WORKS_2\WS\WS_Others.JVEMV6\JVEMV6\44_currency\10_prog-php\2_tester\log_JVE_44_6_2.[session-XXX~].ods	sheet		08.26				*
#	43	observe	trade result list ==> observe / 1) gen list / 2) prep sheet / 3) observe			08.28				*
#	44	coding	“gen trading result list” / 1) as content ==> add : “BUY” or “SELL”	php		08.28				*
#	43.1	observe	trade result list / 1) gen list / 2) prep sheet			08.31				*
#	45	coding	combined data ==> add info / 1) account number	php		09.01				*
#	46	coding	new tester / 1) past X bars ==> all up/down → buy/sell / 2) func name : fx_T_2a_Up_Trend / fx_T_2b_Down_Trend / 3) loc : Lib\utils\fx\lib_ea_tester_2.php	php		09.06				*
#	47	admin	note-pc : setup / 1) new terminal / 2) run 2 terminals; for each, run 1 ea, “detect all”	-		09.08				*
*	48	coding	ea-6.mq4 ==> debug output lines → comment out	mt4		09.13				*
#	48.1	coding	ea-6.mq4 ==> debug output lines → comment out / 1) “cond_OrderModify_1 : ”	mt4		09.14				*
										*
										*
										*
										*
										*
										*
*	*	*	*	*	*	2020/9/18 12:02	2020/9/18 12:02	2020/9/18 12:02	*	*
			2020/9/18 12:02

## 2_qs
sn(3)	description	session id	register	started	comp		*
1	BB.loc-1がBB.2の場合、profit が マイナスのもの、76 % ==> この場合の、BB.loc-2 の場所は、どこだろう？	44#10.3.4_3	20/05/08 14:49				*
2	BB-loc.-1 ~ -3 が 2-2-2 のもの：プラス、マイナス。それぞれ、チャートは、どんな軌跡を描いているか？	44#10.4_7	20/05/16 13:07				*
3							*
							*
							*
							*
							*
							*
							*
							*
							*
							*
							*
							*
*	*	*	2020/9/18 12:02	2020/9/18 12:02	2020/9/18 12:02	*	*

## 3_testers
sn(3)	description	description	session id	register	started	comp		*
1	fx_tester_T_1()	detect pattern ==> all						*
2	fx_tester_T_1__V2()	detect pattern ==> all		05.27				*
3								*
								*
								*
								*
								*
								*
								*
								*
								*
								*
								*
								*
*	*		*	2020/9/18 12:02	2020/9/18 12:02	2020/9/18 12:02	*	*

## 4_stat-items
status	sn(3)	genre	description	platform	session id	register	started	comp		*
	1		table : (gain – loss) : price-wise			09.18				*
	2		table : (gain / total) : num of incidents			09.18				*
	3		chart : period according to entries			09.18				*
			table : total-loss-gain			09.18				*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
										*
*	*	*	*	*	*	2020/9/18 11:57	2020/9/18 11:57	2020/9/18 11:57	*	*
			2020/9/18 11:57